## Sheet1
| Project name | project duration | project start date | project end date
| Lofthus frukt og saft | 25 days | 06.01.2020 | 07.02.2020
Team
Project manager
Tester
Photographer
Developer
Marketing director
Task ID | Task description | Assigned | Task duration | Start date | End date | 06.01.2020 | 07.01.2010 | 08.01.2020 | 09.01.2020 | 10.01.2020 | 13.01.2020 | 14.01.2020 | 15.01.2020 | 16.01.2020 | 17.01.2020 | 20.01.2020 | 21.01.2020 | 22.01.2020 | 23.01.2020 | 24.01.2020 | 27.01.2020 | 28.01.2020 | 29.01.2020 | 30.01.2020 | 31.01.2020 | 03.02.2020 | 04.02.2020 | 05.02.2020 | 06.02.2020 | 07.02.2020
1 | Requirements |  |  |  |  | m | t | w | t | f | m | t | w | t | f | m | t | w | t | f | m | t | w | t | f | m | t | w | t | f
1.2 | Team meeting | Project manager/team | 1 day | 06.01.2020 | 06.01.2020 | bar: m
1.3 | Market reaserch | Marketing director | 0,5 days | 07.01.2020 | 07.01.2020 | bar: t
1.4 | Competetive analysis | Marketing director | 0,5 days | 07.01.2020 | 07.01.2020 | bar: t
1.5 | Create wireframe | Developer | 3 days | 08.01.2020 | 10.01.2020 | bar: w to f
1.6 | Client approval | All stakeholders | 1 day | 10.01.2020 | 10.01.2020 | bar: f
2 | Design
2.1 | Team meeting | Project manager/team | 2 hours | 13.01.2020 | 13.01.2020 | bar: m
2.2 | Website layout | Developer | 4 days | 13.01.2020 | 16.01.2020 | bar: m to t
2.3 | Take photos | Photographer | 2 days | 13.01.2020 | 14.01.2020 | bar: m to t
2.4 | Write content | Marketing director | 2 days | 13.01.2020 | 14.01.2020 | bar: m to t
2.5 | Write product specification | Marketing director | 2 days | 15.01.2020 | 16.01.2020 | bar: w to t
2.6 | Client approval | All stakeholders | 0,5 days | 17.01.2020 | 17.01.2020 | bar: f
3 | Coding
3.1 | Team meeting | Project manager/team | 2 hours | 20.01.2020 | 20.01.2020 | bar: m
3.2 | Create homepage | Developer | 3 days | 20.01.2020 | 22.01.2020 | bar: m to t
3.3 | Create sub-pages | Developer | 7 days | 23.01.2020 | 31.01.2020 | bar: w to f
3.4 | Integrate payment methods | Developer | 2 days | 30.01.2020 | 31.01.2020 | bar: t to f
3.5 | optimization | Developer | 2 days | 03.02.2020 | 04.02.2020 | bar: m to t
3.6 | Validation | Developer | 1 day | 05.02.2020 | 05.02.2020 | bar: w
3.7 | Test | Tester/ developer | 2 days | 05.02.2020 | 06.02.2020 | bar: w to t
3.8 | Client approval | All stakeholders | 0,5 days | 07.02.2020 | 07.02.2020